## Stakeholder Register
Stakeholder Register
Thameswood NHS FT — A&E Patient Flow Improvement Programme ¦ Prepared by Shravan Kanamadi, Business Analyst ¦ 29 June 2026
Stakeholder | Role / Title | Department | Interest in Project | Power | Interest Level | Quadrant (Mendelow) | RACI | Engagement Approach
Director of Urgent & Emergency Care | Programme Sponsor | UEC Division | Accountable for NHS England performance standard delivery and programme outcomes | High | High | Manage Closely | A | Monthly steering board; immediate escalation path for blockers
ED Clinical Lead (Consultant) | Clinical Lead | Emergency Department | Owns clinical safety and workflow design; must approve triage pathway changes | High | High | Manage Closely | R | Weekly working group; co-design sessions for triage redesign
Nursing Workforce Lead | Workforce Lead | Emergency Department | Responsible for nurse staffing rota and impact of any workflow change on shift patterns | High | Medium | Manage Closely | C | Bi-weekly check-in; consulted before any rota-impacting change
Site Operations Manager / Bed Managers | Operational Lead | Site Operations | Executes day-to-day patient flow and bed allocation; primary user of bed-board tool | Medium | High | Keep Informed | R | Daily flow huddle participation; direct feedback loop during pilot
Informatics / BI Team Lead | Technical Lead | Digital & Informatics | Builds and maintains the bed-board tool and Power BI reporting layer | Medium | High | Keep Informed | R | Sprint-based collaboration; included in all technical design reviews
Patient Experience Lead | Advisory | Patient Experience | Represents patient voice; reviews pathway changes for patient-facing impact | Low | Medium | Monitor | C | Consulted at design gate reviews; informed of go-live timing
Finance Business Partner (UEC) | Finance | Finance | Confirms no capital expenditure requirement; tracks any cost avoidance benefit | Medium | Low | Keep Satisfied | I | Informed at programme milestones; sign-off on benefits case
Regional Ambulance Trust Liaison | External Partner | External (Ambulance Service) | Ambulance handover process sits outside trust control but affects front-door volume | Low | Medium | Monitor | I | Informed of relevant changes; no direct engagement required for in-scope work
NHS England Regional Performance Team | External Oversight | External (NHS England) | Monitors trust performance against the 4-hour constitutional standard | High | Low | Keep Satisfied | I | Standard monthly performance submission; no additional engagement required

## Legend
RACI Key
R | Responsible — does the work
A | Accountable — owns the outcome
C | Consulted — provides input
I | Informed — kept up to date
Mendelow Power/Interest Quadrants
Manage Closely | High power, high interest — engage most actively
Keep Satisfied | High power, low interest — keep satisfied, don't overload
Keep Informed | Low power, high interest — keep informed, leverage enthusiasm
Monitor | Low power, low interest — monitor with minimal effort